## Sheet1
2022 ANNUAL ACTION PLAN
SRN | PBB SUB-PROGRAMME | PBB SUB-PROGRAMME | BROAD ACTIVITIES | TIME FRAME (YEAR 2022) |  |  |  | COST | [5 empty] | IMPLEMENTING INSTITUION/DEPT.
|  |  |  | QTR 1 | QTR 2 | QTR 3 | QTR 4 | NEW |  |  | ONGOING
[8 empty] | GOG | IGF | DP | GOG | IGF | DP | LEAD | COLLAB.
1 | ECONOMIC DEVELOPMENT | Agricultural Services and Management | Promote Government Flagship programmes on Agriculture (PFJ, PERD) |  |  |  |  | 10000 |  | 7000 |  |  |  | DoA | DA
2 |  |  | Prepare 2023 MAG AWPB |  |  |  |  | 5000 | [5 empty] | DoA | DA
|  |  | Engage 150 youths on to the Youth in Agriculture programme at Agbateh |  |  |  |  | 50000 | 20000 |  |  |  |  | DoA | Central Admin.
3 |  |  | Facilitate poultry and livestock vaccination District wide | [6 empty] | 4200 |  |  |  | DoA | FBOs
4 |  |  | Build capacity for players in the Agric value chain |  |  |  |  | 10000 |  | 12000 |  |  |  | DOA | HR Dept
5 |  |  | Nurse oil palm, Cashew and citrus seedlings for distribution to farmers District wide |  |  |  |  | 50000 | [5 empty] | DoA | Central Adm.
6 |  |  | Organise pest and Disease surveillance in all operational areas | [6 empty] | 8500 |  |  |  | DoA | FBOs
7 |  |  | Sensitize farmers on Climate smart agriculture, health and child labour related issues |  |  |  |  | 1500 |  | 1600 |  |  |  | DoA | NGOs
8 |  |  | Undertake extension services, monitoring and supervision in all operational areas |  |  |  |  | 76500 |  | 10000 |  |  |  | DoA | FBOs
SUB TOTAL FOR DEPARTMENT OF AGRICULTURE | [7 empty] | 15000 |  | 43300
SRN | PBB SUB-PROGRAMME | PBB SUB-PROGRAMME | BROAD ACTIVITIES | TIME FRAME (YEAR 2022) |  |  |  | COST | [5 empty] | IMPLEMENTING INSTITUION/DEPT.
|  |  |  | QTR 1 | QTR 2 | QTR 3 | QTR 4 | NEW |  |  | ONGOING
[8 empty] | GOG | IGF | DP | GOG | IGF | DP | LEAD | COLLAB.
9 | ECONOMIC DEVELOPMENT | Trade, Tourism and Industrial Development | conduct Youth empowerment programme on entrepreneurship and records keeping |  |  |  |  | 1600 | 2000 | 5000 |  |  |  | BAC | REP/MSEs
10 |  |  | Conduct Business Counseling and Follow up on 50 MSE Clients | [5 empty] | 1500 | 4000 |  |  |  | BAC | REP/MSEs
11 |  |  | Conduct 2 Stakeholders' Forum with MSE Stakeholders |  |  |  |  | 3000 |  | 2000 |  |  |  | BAC | REP
12 |  |  | Facilitate the registration and certification of 30 businesses | [5 empty] | 1000 |  |  |  |  | BAC | DA
13 |  |  | Facilitate 20 MSEs access to finance | [10 empty] | BAC | DA
14 |  |  | Equip 200 youth with technical/vocational and entrepreneurial skills. | [6 empty] | 15000 |  |  |  | BAC | DA
SUB TOTAL FOR BAC | [7 empty] | 4600 |  | 26000
SRN | PBB SUB-PROGRAMME | PBB SUB-PROGRAMME | BROAD ACTIVITIES | TIME FRAME (YEAR 2022) |  |  |  | COST | [5 empty] | IMPLEMENTING INSTITUION/DEPT.
|  |  |  | QTR1 | QTR2 | QTR3 | QTR4 | NEW |  |  | ONGOING
[8 empty] | GOG | IGF | DP | GOG | IGF | DP | LEAD | COLLAB.
15 | Social Services Delivery | Social Welfare and Community Development | Engage 15 Communities on Child protection and promotion activities in 15 selected communities | [6 empty] | 20000 |  |  |  | DSWCD | DA
16 |  |  | Strengthen social protection especially for women and children | [5 empty] | 1500 | 4500 |  |  |  | DSWCD | DA
17 |  |  | Rescue abandoned/trafficked children |  |  |  |  | 3000 | 2000 |  |  |  |  | DSWCD | DA
18 |  |  | Attend 48 juvenile / family tribunal court sitting at Peki |  |  |  |  | 1500 | [5 empty] | DSWCD | DA
19 |  |  | Strengthen access for vulnerable groups to justice, rights and entitlements |  |  |  |  | 4000 | [5 empty] | DSWCD | DA
20 |  |  | Provide assistive device and equipment for PWD |  |  |  |  | 50000 | [5 empty] | DSWCD | DA
21 |  |  | Provide educational /health support for PWD and strengthen social protection |  |  |  |  | 7000 | [5 empty] | DSWCD | DA
22 |  |  | Provide financial support for PWD |  |  |  |  | 3000 | [5 empty] | DSWCD | DA
23 |  |  | Educate students of second cycle institutions on gender-based violence |  |  |  |  | 3000 | [5 empty] | DSWCD | GES
24 |  |  | Pay LEAP grants to beneficiaries bi-quarterly |  |  |  |  | 205000 | [5 empty] | DSWCD | DA
25 |  |  | Strengthen institutional arrangement for expansion and inclusion of vulnerable groups |  |  |  |  | 2000 | [5 empty] | DSWCD | DA
SUB TOTAL FOR SOCIAL DEVELOPMENT | [7 empty] | 275500 |  | 24500
SRN | PBB SUB-PROGRAMME | PBB SUB-PROGRAMME | BROAD ACTIVITIES | TIME FRAME (YEAR 2022) |  |  |  | COST | [5 empty] | IMPLEMENTING INSTITUION/DEPT.
|  |  |  | QTR 1 | QTR 2 | QTR 3 | QTR 4 | NEW |  |  | ONGOING
[8 empty] | GOG | IGF | DP | GOG | IGF | DP | LEAD | COLLAB.
25 | Social Services Delivery | Education, Youth and Sports Services | Support District Level Inter Circuit Sports |  |  |  |  | 3000 |  | 20000 |  |  |  | GES | DA
26 |  |  | Organize Capacity building workshop for TVET teachers and women in Tech education programme |  |  |  |  | 3000 | [5 empty] | GES | DA
27 |  |  | Strengthen STMIE clinics in Schools each year to increase performance |  |  |  |  | 12000 | [5 empty] | GES | DA
28 |  |  | Sensitization on importance of Education for girl child | [10 empty] | GES | DA
29 |  |  | Conduct supervision and monitoring of educational delivery in the district | [10 empty] | GES | DA
30 |  |  | Provide 1000 dual desk to support 15 public schools. |  |  |  |  | 50000 | [5 empty] | GES | DA
31 |  |  | Organise Workshop on preparation of ADEOP, ADPRand staff and headmasters on EMIS Questionnaire | [10 empty] | GES | DA
32 |  |  | Organise Carols/choral festival |  |  |  |  | 3000 | [5 empty] | GES | DA
33 |  |  | Identify and profile three tourist sites |  |  |  |  | 4500 | [5 empty] | GES | DA
34 | [7 empty] | 75500 |  | 20000
35 | PBB PROGRAMME | PBB SUB-PROGRAMME | BROAD ACTIVITIES | TIME FRAME (YEAR 2022) |  |  |  | COST | [5 empty] | IMPLEMENTING INSTITUION/DEPT.
36 |  |  |  | QTR 1 | QTR 2 | QTR 3 | QTR 4 | NEW |  |  | ONGOING
37 | [7 empty] | GOG | IGF | DP | GOG | IGF | DP | LEAD | COLLAB.
38 | Social Services Delivery | Public Health Services and Management | Organise training on nutrition for food vendors and school feeding contractors |  |  |  |  | 2000 |  | 20000 |  |  |  | DDHS | DEHO/DA
39 |  |  | Promote Nutrition oriented intervention programmes | [10 empty] | DDHS | SWCD
40 |  |  | Establish four (4) adolescent clubs in SHS |  |  |  |  | 1000 | [5 empty] | DDHS | DEHO/DA
41 |  |  | Establish four (4) adolescent clubs in SHS |  |  |  |  | 2000 | [5 empty] | DDHS | DA
42 |  |  | Organize quarterly EPI mop-up activity in all communities to improve immunization coverage |  |  |  |  | 2000 | [5 empty] | DDHS | DA
43 |  |  | Procure and distribute PPES to 4 selected CHPS compounds |  |  |  |  | 2000 | [5 empty] | DA | DDHS
44 |  |  | Suspect and investigate priority diseases, such as Measles, Yellow Fever, AFP, COVID-19 |  |  |  |  | 2000 | [5 empty] | DDHS | DA
45 |  |  | District response initiative on HIV/AIDS and malaria control |  |  |  |  | 32877.94 | 1000 |  |  |  |  | GHS | DA
46 |  | Birth and Death Registration Services | Conduct monthly Births and Deaths Registration at 30 weighing /community centers |  |  |  |  | 8000 | [5 empty] | DoB&D | DA
47 |  |  | Provide 3No. Signpost/Signpost for the Department Peki and Dzemeni |  |  |  |  | 6000 | [5 empty] | DoB&D | DA
48 |  |  | Conduct Mass /Mop up registration in 10 communities |  |  |  |  | 5500 | [5 empty] | DoB&D | DA
SUB TOTAL FOR HEALTH | [7 empty] | 61377.94
SRN | PBB SUB-PROGRAMME | PBB SUB-PROGRAMME | BROAD ACTIVITIES | TIME FRAME (YEAR 2022) |  |  |  | COST | [5 empty] | IMPLEMENTING INSTITUION/DEPT.
|  |  |  | QTR 1 | QTR 2 | QTR 3 | QTR 4 | NEW |  |  | ONGOING
[8 empty] | GOG | IGF | DP | GOG | IGF | DP | LEAD | COLLAB.
49 | Social Services Delivery | Environmental Health and Sanitation Services | Legally acquire and manage one site 4 acres each for final liquid waste disposal in the district at Tsatee and Todome |  |  |  |  | 50000 | [5 empty] | DEHO | DA
50 |  |  | Acquire 2 refuse containers and 100 household dust bins and distribute to land lords |  |  |  |  | 15000 | [5 empty] | DEHO | DA
51 |  |  | Rehabilitate the slaughter house and meat shop and fence them Kpeve and Dzemeni |  |  |  |  | 25000 | [5 empty] | DEHO | DWD/DA
52 |  |  | Carry out Spraying /fumigation of pest infested verminous premises |  |  |  |  | 6500 | [5 empty] | DEHO | DA
53 |  |  | Update newly prepared DESSAP from 2022-2025 |  |  |  |  | 10000 | [5 empty] | DEHO | DA
54 |  |  | Organize monthly communal labour and control of stray animals |  |  |  |  | 5000 | [5 empty] | DEHO | DA
55 |  |  | Carry out premises inspection health education promulgation of bye laws |  |  |  |  | 2000 | [5 empty] | DEHO | DA
56 |  |  | To pre trigger, trigger and carry out verification in 15 CLTS communities and declare them ODF |  |  |  |  | 5000 | [5 empty] | DEHO | DA
57 |  |  | procure 3 number motor bikes, 1spraying machine and 1noise meter and disinfectants/detergents |  |  |  |  | 70000 | [5 empty] | DEHO | DA
58 |  |  | Carry out dislodging of full up latrines |  |  |  |  | 20000 | [5 empty] | DEHO | DA
208500
| Development Dimension: Environment, Infrastructure and Human Settlement | [7 empty] | Focus Area: Protected Areas
61 | PBB SUB-PROGRAMME | PBB SUB-PROGRAMME | BROAD ACTIVITIES | TIME FRAME (YEAR 2022) |  |  |  | COST | [5 empty] | IMPLEMENTING INSTITUION/DEPT.
62 |  |  |  | QTR1 | QTR2 | QTR3 | QTR4 | NEW |  |  | ONGOING
63 | [7 empty] | GOG | IGF | DP | GOG | IGF | DP | LEAD | COLLAB.
64 | Environmental Management | Disaster Prevention and Management | organize sensitization programmes for disaster prevention and NADMO's mandate for identified stakeholders |  |  |  |  | 15000 | [5 empty] | NADMO | DA
65 |  |  | Undertake tree planting exercises at identified locations |  |  |  |  | 5000 | [5 empty] | DA/NADMO | NGOs
66 |  |  | Emmergency preparedness and response to disaster |  |  |  |  | 5000 | [5 empty] | DA/NADMO | DA
67 |  |  | Support for Community Resource Management Area Groups |  |  |  |  | 5000 | [5 empty] | NADMO | DA
SUB TOTAL FOR NADMO | [7 empty] | 30000
SRN | Development Dimension: Environment, Infrastructure and Human Settlement | [7 empty] | Focus Area: Protected Areas
| PBB SUB-PROGRAMME | PBB SUB-PROGRAMME | BROAD ACTIVITIES | TIME FRAME (YEAR 2022) |  |  |  | COST | [5 empty] | IMPLEMENTING INSTITUION/DEPT.
|  |  |  | QTR 1 | QTR 2 | QTR 3 | QTR 4 | NEW |  |  | ONGOING
[8 empty] | GOG | IGF | DP | GOG | IGF | DP | LEAD | COLLAB.
68 | Infrastructure Delivery and Management | Public Works, Rural Housing and Water Management | Reshaping of selected feeder roads 78km |  |  |  |  | 50000 | [5 empty] | DWD | DA
69 |  |  | Complete the construction of market stall at Gbi market | [7 empty] | 60000 |  |  | DWD | DA
70 |  |  | Complete the Construction of 2No. Culverts and graveling and reshaping of 1.2km road from Health Directorate-Tsokpokope road and Desilting of river Amemle | [7 empty] | 70000 |  |  | DWD | DA
71 |  |  | Complete the Construction of area council Office | [7 empty] | 325489.8 |  |  | DWD | DA
72 |  |  | Construction of two No. pound at Dzemeni and Peki |  |  |  |  | 38000 | [5 empty] | DWD | DA
73 |  |  | Construction of platform for cassava dough sellers and 2no Urinal for Kpeve and dzemeni market. |  |  |  |  | 25000 | 3000 |  |  |  |  | DWD | DA
74 |  |  | Complete the Construction of 1No 3-unit classroom block at Kpalime Duga | [6 empty] | 331658 |  |  |  | DWD | DA
75 |  |  | Maintain DA building, furniture and other DA properties |  |  |  |  | 30000 | [5 empty] | DWD | DA
76 |  |  | Renovation of revenue post at Dzemeni and extension of electricity to Kpeve revenue post |  |  |  |  | 20000 | [5 empty] | DWD | Finance
77 |  |  | Extension of Electricity to revenue post in Kpeve and procurement of 2No wheel clamp to arrest drivers for wrong packing |  |  |  |  | 5200 | [5 empty] | DWD | Finance
78 |  |  | Complete Drilling and Construction of 5 No. Mechanized Boreholes and organize WATSAN for newly constructed Boreholes. | [7 empty] | 183530 |  |  | DWD | DA
79 |  |  | Support for Self Help Projects |  |  |  |  | 100000 | [5 empty] | DWD | DA
80 |  |  | construction of 2No. Office accommodation |  |  |  |  | 650000 | [5 empty] | DWD | DA
81 |  |  | Construction of 1No 5units chamber and Hall Teachers Bungalow in Peki Dzake |  |  |  |  | 400000 | [5 empty] | DWD | DA/GHS
82 |  |  | Rehabilitate the DA Garage and build additional rooms |  |  |  |  | 15000 | 12000 |  |  |  |  | DWD | DA
TOTAL FOR WORKS DEPARTMENT | [7 empty] | 1561730 | 15000 | 331658
SRN | PBB SUB-PROGRAMME | PBB SUB-PROGRAMME | BROAD ACTIVITIES | TIME FRAME (YEAR 2022) |  |  |  | COST | [5 empty] | IMPLEMENTING INSTITUION/DEPT.
|  |  |  | QTR 1 | QTR 2 | QTR 3 | QTR 4 | NEW |  |  | ONGOING
[8 empty] | GOG | IGF | DP | GOG | IGF | DP | LEAD | COLLAB.
83 | Infrastructure Delivery and Management | Physical and Spatial Planning Development | a. Identify, demarcate and register Assembly lands |  |  |  |  | 20000 | [5 empty] | PPD | DA
84 |  |  | Education campaigns and awareness creation on Spatial planning, permitting procedures, street naming and digital addressing. |  |  |  |  | 3000 | 2500 |  |  |  |  | PPD | DA
85 |  |  | Prepare Planning Schemes for the district |  |  |  |  | 50000 | [5 empty] | PPD | DA
86 |  |  | Procure 1No mower |  |  |  |  | 2000 | [5 empty] | Parks and Gardens | PPD
87 |  |  | Organize capacity building on GIS software |  |  |  |  | 5000 | [5 empty] | PPD | DA
88 |  |  | Beautification of South Dayi District Assembly and DCE’s Bungalow and Undertake Propagation |  |  |  |  | 6000 | [5 empty] | Parks and Gardens | PPD/DA
89 | [7 empty] | 80000 | 2500
90 | PBB SUB-PROGRAMME | PBB SUB-PROGRAMME | BROAD ACTIVITIES | TIME FRAME (YEAR 2022) |  |  |  | COST | [5 empty] | IMPLEMENTING INSTITUION/DEPT.
91 |  |  |  | QTR 1 | QTR 2 | QTR 3 | QTR 4 | NEW |  |  | ONGOING
92 | [7 empty] | GOG | IGF | DP | GOG | IGF | DP | LEAD | COLLAB.
93 | Management and Administration | Planning, Budgeting, Coordination and Statistics | Training on methods and statistical concept and undertake multi sectoral data collection. |  |  |  |  | 4000 | [5 empty] | Statistics | DA
94 |  |  | Procure 1no swivel chair, 1no core i5 laptop computer and internet router for the department |  |  |  |  | 15000 | [5 empty] | Statistics
95 |  |  | Collaborate with Births and Deaths Registry, DEHO and other departments and institutions for harmonization of data and population projection and disseminate for decision making |  |  |  |  | 3000 | [5 empty] | Statistics | DA
TOTAL FOR STATISTICS DEPARTMENT | [7 empty] | 22000
SRN | PBB SUB-PROGRAMME | PBB SUB-PROGRAMME | BROAD ACTIVITIES | TIME FRAME (YEAR 2022) |  |  |  | COST | [5 empty] | IMPLEMENTING INSTITUION/DEPT.
|  |  |  | QTR 1 | QTR 2 | QTR 3 | QTR 4 | NEW |  |  | ONGOING
[8 empty] | GOG | IGF | DP | GOG | IGF | DP | LEAD | COLLAB.
96 | Management and Administration | : Human Resource Management | Procurement of 120 ID Cards for Staff |  |  |  |  | 75000 | 1000 |  |  |  |  | HRD | DA
97 |  |  | Implement 9 Capacity building interventions |  |  |  |  | 105000 | [5 empty] | HRD | DA
98 |  |  | Submission of reports and validate salaries of mechanized staff |  |  |  |  | 40000 | [5 empty] | HRD | CA
TOTAL FOR HUMAN RESOURCE DEPARTMENT | [7 empty] | 220000 | 1000
SRN | PBB SUB-PROGRAMME | PBB SUB-PROGRAMME | BROAD ACTIVITIES | TIME FRAME (YEAR 2022) |  |  |  | COST | [5 empty] | IMPLEMENTING INSTITUION/DEPT.
|  |  |  | QTR 1 | QTR 2 | QTR 3 | QTR 4 | NEW |  |  | ONGOING
[8 empty] | GOG | IGF | DP | GOG | IGF | DP | LEAD | COLLAB.
99 | Management and Administration | General Administration | Website maintenance, updates and Internet Data Package management and software licenses and updates |  |  |  |  | 10000 | [5 empty] | IT | DA
100 |  |  | Procure 1no 5000L Rambo tank for water storage |  |  |  |  | 15000 | [5 empty] | CA | DA
101 |  |  | Provision Of office stationery and logistics (Printer, Desktop, Address |  |  |  |  | 30000 | [5 empty] | CA | DA
102 |  |  | Pay for NALAG Contributions |  |  |  |  | 6376.64 | [5 empty] | CA | DA
103 |  |  | Engage 12 traditional Areas |  |  |  |  | 60000 | [5 empty] | CA | DA
104 |  |  | Support needy but brilliant students |  |  |  |  | 50000 | [5 empty] | DA | MP
105 |  |  | Procurement of office Equipment for Tongor Kpalime Area and Peki Town Councils |  |  |  |  | 40000 | [5 empty] | DA | CA
106 |  |  | Running cost, maintenace and insurance of Official Vehicles |  |  |  |  | 71500 | [5 empty] | CA | Insurance co
107 |  |  | Uniforms and Accoutrement for revenue collectors, security and sanitary officers |  |  |  |  | 5000 | [5 empty] | CA | Finance dept
108 |  |  | Embossment and Labelling of all Assembly Physical Projects |  |  |  |  | 25000 | [5 empty] | CA | Procurement unit
109 |  |  | Procure 1no power generator for the Assembly |  |  |  |  | 20000 | [5 empty] | CA | Procurement unit
110 |  |  | Procurement of 1No. Pick up and 2no. Motor bikes for revenue mobilization |  |  |  |  | 50000 | 20000 |  |  |  |  | CA | Finance dept
111 |  |  | Training/Orientation of revenue collectors on revenue mobilization strategies and fee-fixing | [10 empty] | Finance Dept | CA
112 |  |  | Conduct monthly monitoring of revenue collectors |  |  |  |  | 10000 | [5 empty] | Finance Dept | CA
113 |  |  | Payment of Utility charges |  |  |  |  | 40000 | 4000 |  |  |  |  | CA | Finance dept
114 |  |  | Organization of Quarterly Performance and statutory Meetings of the Assembly |  |  |  |  | 1000 | [5 empty] | DA | CA
115 | Management and Administration | Planning, Coordination and Statistics | Organization of Forum on Public Financial Management (PFM) |  |  |  |  | 5000 | [5 empty] | PLG Unit | DA
116 |  |  | Implementation of NACAP 2022 |  |  |  |  | 12000 | [5 empty] | CA | DA
117 |  |  | prepare 2023-2026 MTEF and fee-fixing resolution |  |  |  |  | 10000 | [5 empty] | PLG Unit | DA
118 |  |  | Complete preparation of 2022-2025 MTDP |  |  |  |  | 60000 | [5 empty] | PLG Unit | DA
119 |  |  | Official and International Day Celebrations |  |  |  |  | 60000 | [5 empty] | DA | DA
120 |  |  | Conduct Monitoring and Evaluation |  |  |  |  | 12500 | 24000 |  |  |  |  | PLG Unit | DA
TOTAL FOR CENTRAL ADMINISTRATION | [7 empty] | 593376.64 | 48000

## Sheet3
Laptops
Finance 1
2 stats
1Stats
1RMU Desktop, Canon bed scaner
Budget 1

## 2024 AAP
SOUTH DAYI DISTRICT ASSEMBLY
2023 ANNUAL ACTION PLAN
SRN | PBB PROGRAMME | PBB SUB-PROGRAMME | BROAD ACTIVITIES | LOCATION | TIME FRAME |  |  |  | COST |  |  | PROGRAMME STATUS |  | IMPLEMENTING INSTITUION
/DEPT.
[5 empty] | QTR 1 | QTR 2 | QTR3 | QTR4 | GOG | IGF | OTHERS | NEW | ON-GOING | LEAD | COLLAB.
1 | ECONOMIC DEVELOPMENT | Agricultural Services and Management | Embark on pest and disease surveillance, public education on zoonotic diseases and mass rabbies vaccination | District wide | [6 empty] | 2000 |  |  | DoA | DA
2 |  |  | Establish 4 demonstration on 12 steps maize production | 4 selected communities | [6 empty] | 5000 |  |  | DoA | DA
3 |  |  | Sensitize farmers on climate SMART agriculture | District wide | [6 empty] | 2000 |  |  | DoA | DA
4 |  |  | Introduce coping strategies for women famers in the District. | District wide | [6 empty] | 5000 |  |  | DoA | BAC/BRC/DA
5 | ECONOMIC DEVELOPMENT |  | Facilitate sensitization on the harmful effects of using lorry tyres for singeing animals at the slaughter houses, meat processing points and farmers on health and child labour related issues. | Kpeve, Peki and Dzemeni | [6 empty] | 3000 |  |  | DoA | DA
6 |  |  | Train producers, processors and marketers 4FBOs in standardization, packaging and branding | District wide | [6 empty] | 2000 |  |  | DoA | HRM/DA
7 |  |  | Procure 2no. Mobile maize sheller and a tractor for the district. | District wide | [6 empty] | 4000 |  |  | DoA | DA
3DAOs monitor agricultural activities of farmers in the district.
9 | ECONOMIC DEVELOPMENT | Trade and Industrial Development | Conduct 2 Stakeholders' Forum with MSE Stakeholders | Kpeve |  |  |  |  | 10000 |  |  |  |  | BAC/NBSSI | DA
11 |  |  | Equip 20 youth with technical and vocational skills. | District wide |  |  |  |  | 10000 |  |  |  |  | BAC/NBSSI | DA
12 |  |  | Facilitate and Support micro, small and medium scale enterprises for creation of new businesses | District wide |  |  |  |  | 50000 |  |  |  |  | BAC/NBSSI | DA/DoA
13 |  |  | conduct Youth empowerment programme on entrepreneurship and records keeping | District wide |  |  |  |  | 5000 |  |  |  |  | BAC/NBSSI | DA/DoA
14 | SOCIAL SERVICES DELIVERY | Social Welfare and Community Development | Engage 15 Communities on Child labor, Trafficking, Adolescent Pregnancy and Child marriage (Child protection) | District wide | [6 empty] | 20000 |  |  | SWCD | CHRAJ/NCCE/DA
15 |  |  | Train 10 social service providers on the ISSOP | Kpeve | [6 empty] | 5000 |  |  | SWCD/HRM | DA
16 |  |  | Provide support for 10 Children in Conflict with the Law | District wide |  |  |  |  | 6000 |  |  |  |  | SWCD | DA
17 |  |  | Rescue 4abandoned, 6missing and trafficked children | District wide |  |  |  |  | 2000 |  |  |  |  | SWCD | DA
18 |  |  | Educate students of second cycle institutions on gender-based violence and its related issues and provide guidance and counselling and social support to victims | District wide |  |  |  |  | 5000 |  |  |  |  | SWCD | DA
19 |  |  | Sensitize 5 communities on Adolescent Commercial sex exploitation | District wide |  |  |  |  | 5000 |  |  |  |  | SWCD | DA
20 |  |  | Facilitate the payment of LEAP grants to beneficiaries bi-monthly | District wide | [5 empty] | 3000 |  |  |  | SWCD | DA
21 |  |  | Organize literacy and adult education program in Kaira and Sanga | Kaira and Sanga | [5 empty] | 3000 |  |  |  | SWCD/CEA | DA
23 |  |  | Provide educational, skill training and financial support for PWD | District wide |  |  |  |  | 10000 |  |  |  |  | SWCD | DA
24 |  |  | Conduct needs assessment and Provide health and economic support including assistive devices and equipments for PWD | District wide |  |  |  |  | 140000 |  |  |  |  | SWCD | DA
26 | SOCIAL SERVICES DELIVERY | Public Health Services and Management | Organise training on nutrition for food vendors and school feeding contractors | District wide |  |  |  |  | 3000 |  |  |  |  | GHS | DA
27 |  |  | Promote Nutrition oriented intervention programmes through sensitization | District wide |  |  |  |  | 2000 |  |  |  |  | GHS | DA
28 |  |  | District response initiative on HIV/AIDS and malaria control | District wide |  |  |  |  | 32877.94 |  |  |  |  | GHS | DA
29 |  |  | Investigate suspected priority diseases, such as Measles, Yellow Fever, AFP, COVID-19 | Selected communities | [5 empty] | 2000 |  |  |  | GHS | DA
30 |  |  | Support to 3 health facilities with bed infrastructure, extension of electricity and water | 3 selected communities |  |  |  |  | 30000 |  |  |  |  | GHS | DA
31 |  |  | Organise quarterly Public Health Emergency Management Committee Meeting | Kpeve | [5 empty] | 3800 |  |  |  | GHS | DA
32 | SOCIAL SERVICES DELIVERY | Birth and Death Registration Services | Conduct monthly sensitization and Births and Deaths Registration at weighing /all communities | District wide |  |  |  |  | 8000 |  |  |  |  | B&D REGISTRY | DA
34 |  | Education, Youth & Sports Services | Sensitisation on importance of Education for girl child | District wide |  |  |  |  | 5000 |  |  |  |  | GES/SWCD | DA
35 |  |  | Organize Capacity building workshop for TVET teachers and women in Tech education programme | Kpeve |  |  |  |  | 3000 |  |  |  |  | GES | DA
36 |  |  | Support District Level Inter Circuit Sports | Kpeve |  |  |  |  | 3000 |  |  |  |  | GES | DA
37 |  |  | Support for preparation of ADEOP, ADPR and staff and headmasters on EMIS Questionaire | Kpeve | [5 empty] | 2500 |  |  |  | GES | DA
38 | SOCIAL SERVICES DELIVERY | Environmental Health and Sanitation Services | Pre trigger, trigger and carry out verification in 6 CLTS communities and declare them ODF | 6 selected communities |  |  |  |  | 10000 |  |  |  |  | EHU | DA
39 |  |  | Engage key stakeholders and acquire ten acres land for solid waste disposal site at Tsatee | Tsatee |  |  |  |  | 60000 |  |  |  |  | EHU | DA
|  |  | Pay for fumigation and sanitation improvement package | District wide |  |  |  |  | 165000
|  |  | Medical screening for persons engaged in the hospitality industry. | District wide
|  |  | Management of final solid waste disposal site | Tsatee
|  |  | Liquid waste management | Akrofu
40 |  |  | Organize monthly communal labour and control of stray animals | District wide | [5 empty] | 5000 |  |  |  | EHU | DA
|  |  | Premises inspection, health education and enforcement of laws | District wide
41 | ENVIRONMENTAL MANAGEMENT | Disaster Prevention and Management | Organize sensitisation programmes for disaster prevention and NADMO's mandate for identified stakeholders | District wide |  |  |  |  | 10000 | 10000 |  |  |  | NADMO | DA
43 |  | Natural Resource Conservation and Management | Organize campaign against bush fire in 21 electoral areas. | District wide |  |  |  |  | 5000 | 4000 |  |  |  | NADMO | DA
44 |  |  | Undertake tree planting response to Green Ghana initiatives. | District wide |  |  |  |  | 10000 |  |  |  |  | DA | CREMA GROUPS
|  |  | Stockpiling of items for disaster victims | District wide |  |  |  |  | 50000
46 | INFRASTRUCTURE DELIVERY AND MANAGEMENT |  | Reshaping of 15km roads District Wide and construction of culverts on selected roads in the district. | District wide |  |  |  |  | 300000 |  | 100000 |  |  | DWD | DA
47 |  |  | Complete the construction of Area Council Office at Tongor Tsanakpe | Tongor Tsanakpe |  |  |  |  | 249741.7 |  |  |  |  | DWD | DA
48 |  |  | Complete Drilling and Construction of 5 No. Mechanised Boreholes and organize WATSAN for newly constructed Boreholes. | 5 selected communities |  |  |  |  | 79326.8 |  |  |  |  | DWD | DA
49 |  |  | Renovation of 6-unit classroom block at Agbateh | Agbateh |  |  |  |  | 300000 |  |  |  |  | DWD | DA
|  |  | Procurement and installation of 25No. Street signages | District wide |  |  |  |  | 40000 |  |  |  |  | DWD | DA
|  |  | Construction of 4No Teachers Quarters at Peki Dzake | Peki Dzake | [6 empty] | 593564.5 |  |  | DWD | DA
52 |  |  | Maintain DA properties, and public places of interest (Slaughter HSE Dzemeni, Rehab building for transitional shelter in Kpeve etc) | Kpeve Newtown |  |  |  |  | 300000 |  |  |  |  | DWD | DA
54 |  |  | Construction of 1no 2-Unit KG block at Agordeke | Agordeke |  |  |  |  | 300000 |  |  |  |  | DWD | DA
|  |  | Repair of Office buildings and Renovation of Residential Buildings | Kpeve |  |  |  |  | 90000 |  |  |  |  | DWD | DA
55 |  |  | Support for the contruction of accident center at Peki | Peki Government Hospital |  |  |  |  | 80000 |  |  |  |  | DWD | DA
56 |  |  | Support for Self Help Projects | District wide |  |  |  |  | 160000 |  |  |  |  | DWD | DA
|  |  | complete 10 seater WC( Kpeve) | Kpeve | [5 empty] | 150000 |  |  |  | DWD | Sub-structures
58 |  | Physical and Spatial Planning Development | Erect 8 signpost (B&D) and speed bumps in selected communities | Selected Communities |  |  |  |  | 10000 |  |  |  |  | PPD/DWD/D&D | DA
59 |  |  | Identify, demarcate and register Assembly lands | District wide |  |  |  |  | 60000 |  |  |  |  | PPD/DWD | DA
60 |  |  | Education campaigns and awareness creation on Spatial planning, permitting procedures, street naming and digital addressing. | District wide |  |  |  |  | 7000 |  |  |  |  | PPD | DA
|  |  | Grassing and beautification of Assembly premises | Kpeve |  |  |  |  | 11983.07 |  |  |  |  | Parks and Gardens | PPD
61 |  |  | Prepare local plans for 2 communities and base maps for Planning Schemes for 2communities | Selected Communities |  |  |  |  | 70000 |  |  |  |  | PPD | DA
62 |  |  | Capacity Building for staff on GIS software | Kpeve |  |  |  |  | 10000 |  |  |  |  | PPD | DA
63 | MANAGEMENT AND ADMINISTRATION | Finance and Audit | Complete payment of 1No. Pick up for revenue mobilization | Kpeve |  |  |  |  | 70000 |  |  |  |  | FINANCE | DA
64 |  |  | Conduct monthly monitoring of revenue collecters | Kpeve, Peki and Dzemeni |  |  |  |  | 10000 | 5000 |  |  |  | FINANCE | DA
66 |  |  | Conduct a survey on all businesses that are in operation and those unfolding for revenue improvement | District wide |  |  |  |  | 5000 |  |  |  |  | STATS/FIN/DPCU | DA
69 |  |  | Procure 120 no ID cards for staff | Kpeve |  |  |  |  | 6000 |  |  |  |  | HRM | DA
70 |  |  | Implement Capacity building interventions | Kpeve |  |  |  |  | 30000 |  | 50000 |  |  | HRM | DA
71 |  | General Administration | Organization of 2townhall meetings on workplan and budget performance and preparation of 2025 workplan and budget. | District wide |  |  |  |  | 13000 |  |  |  |  | CA | DA
72 |  |  | Implementation of NACAP 2024 | District wide |  |  |  |  | 12000 |  |  |  |  | CHRAJ/NCCE/CA,POLICE | DA
73 |  |  | Prepare 2025-2029 MTEF and fee-fixing resolution | Kpeve |  |  |  |  | 25000 |  |  |  |  | PLG UNIT | DA
74 |  |  | Official and International Day Celebrations | District wide |  |  |  |  | 30000 |  |  |  |  | CA | DA
75 |  |  | Organisation of Quarterly Performance, Staff Durbars and statutory Meetings of the Assembly | Kpeve |  |  |  |  | 90000 | 20000 |  |  |  | CA | DA
76 |  |  | Running cost, maintenace and insurance of Official Vehicles and payment of utility | Kpeve |  |  |  |  | 90000 | 20000 |  |  |  | CA | DA
77 |  |  | Engage 4 traditional Areas as part of DCE's engagement with at least 15% of communities. | District wide |  |  |  |  | 60000 |  |  |  |  | CA | DA
78 |  |  | Pay for NALAG Contributions | Kpeve |  |  |  |  | 7000 |  |  |  |  | CA | DA
79 |  |  | Procure 1no 5000L rambo tank for water storage | Kpeve |  |  |  |  | 15000 |  |  |  |  | CA | DA
80 |  |  | Build,mainatainance,update DA website, purchase Internet Data Packages and aquire software licences and updates | Kpeve |  |  |  |  | 15000 |  |  |  |  | MIS/CA | DA
82 |  |  | Procurement of office equipment, logistics, and stationaries. | Kpeve |  |  |  |  | 100000 |  |  |  |  | CA | DA
83 |  |  | Procurement of office Equipment for Tongor Kpalime Area and Peki Town Councils | Kpeve |  |  |  |  | 40000 | 10000 |  |  |  | CA | DA
84 |  |  | Conduct midterm evaluation of the 2022-2025 MTDP | Kpeve |  |  |  |  | 60000 |  |  |  |  | PLG UNIT | DA
85 |  |  | Conduct quarterly DPCU Monitoring and Evaluation | Kpeve |  |  |  |  | 50000 |  |  |  |  | PLG UNIT | DA

## DEV'T DIMENSIONS
Economic Develeopment | 13
Social Development | 24 | 84
Environment,Infrastructure and human settlement | 22 |  | 84
Governance, Corruption and public accountability | 25
EMERGENCY PLANNING AND RESPONSE (INCLUDING COVID-19 RECOVERY PLAN) | 84
IMPLEMENTATION, COORDINATION, MONITORING AND EVALUATION
COVID-19
Ghana's Role in International Relations
AREAS OF NEEDS PLANNED
Environmental Health, Sanitation & Climate change
Local Economic Development
Capacity Building
Revenue Generation
Social Protection, Gender and Nutrition
Physical and spatial planning services
Transparency, Accountability, and Participation: DCE'S tour, NACAP, Forums on Plan and budget, PRCC and Client service activities
Operations and maitenance
Tourism